## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2231-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | Your team name as "term-swen-261-sec-letter name", e.g. 2231-swen-261-10-a Speedy Racers
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a helper I want to see a list of needs so that I choose what to contribute to. | Given that I am on the u-fund site when I am not on the Needs page then I must see a means to navigate to the Needs page. |  | JM 10/26/23 |  | JM 11/9/23
| Given that I am not on the Needs page when I choose the Needs page then I am taken to the Needs page. |  | JM 10/26/23 |  | JM 11/9/23
| Given that I am on the Needs page when there are no needs in the cupboard I see a message indicating that that there are no needs available to contribute. |  | JM 10/26/23, No message is displayed but a correctly empty cupboard is present |  | JM 11/9/23 Message remains not present
| Given that I am on the Needs page when there are needs in the cupboard then I see each need and short description. |  | JM 10/26/23 |  | JM 11/9/23
| Given that I am on the Needs page when there are needs in the cupboard then I see a means to add each need to my funding basket. |  | JM 10/26/23 |  | JM 11/9/23
| **Given** I am searching the Cupboard **when** I press "Add to Funding Basket" **then** I have the Need added to my cart and I'm kept on the cupboard. |  | JM 10/26/23 |  | JM 11/9/23
| **Given** I have an item in my funding basket **when** I press the remove button **then** the item will be removed from my funding basket. |  | JM 10/26/23 |  | JM 11/9/23
Useer login | **Given** I am a helper** when** I log in **then** I can edit my funding basket. |  | JM 10/26/23 |  | JM 11/9/23
| **Given** I am a U-Fund manager **when** I log in with the username 'admin' **then** I can edit my cupboard. |  | JM 10/26/23 |  | JM 11/9/23
| Given I have a need, I can add said need to the Checkout. |  | JM 10/26/23 |  | JM 11/9/23
As a helper I want to receive rewards based on donations so that I am incentivized to donate more. | **Given** I am a helper and I have a sufficient amount of "points" **when** I checkout a need **then** I can use the "points" to pay for the need. |  | JM 10/26/23 FAIL, reward system not implemented |  | JM 11/9/23 FAIL, not implemented
| **Given** I am a helper on the site **when** I checkout with needs **then** I get a small amount of "points". |  | JM 10/26/23 FAIL, reward system not implemented |  | JM 11/9/23 FAIL, not implemented
As a U-Fund manager I want to match helper donations during certain events so that helpers are incentivized to donate more. | **Given** a user **when** they make a donation**then** the admin automatically meets that donation. |  |  |  | JM 11/9/23 FAIL, not implemented
As a User I want to an independent basket so that it can be persistent. | **Given** A user exists **when** they access their funding basket **then** that basket is specific to them. |  |  |  | JM 11/9/23 UNTESTED, code exists but unable to test without access to multiple accounts.
As a Helper I want to inventory to update when I checkout so that my contributions are recorded. | **Given** A user **when** they proceed to checkout **then** need inventory is properly updated. |  |  |  | JM 11/9/23
As a User I want to search needs using case sensitivity so that the search is refined. | **Given** a user **when** they search for a need **then** they receive information on that need if it exists . |  |  |  | JM 11/9/23 Need searching exists but does not appear to be case sensitive.
As a non User I want to register an account so that I can be a User. | **Given** I am a user **when** I don't have an account **then** I am able to register a new account. |  |  |  | JM 11/9/23 Apears to be implemented correctly, requires further testing.